## Slide 1: Outline
Current State
Thesis Expectations
  Experiments
  Timeline
  MONAI Contributions
Future Communication Expectations
Academic Advising

## Slide 2: Current State
Done
  Image & FCSV Loading
  Replay Memory
  Landmark Environment
  Hard-parameter Sharing Network Architecture
  Agent Optimization – AC on one image
Next Steps
  Two stage detection
  Explore Supervised methods
Notes: Check float percisions
Check Agent optimization across multiple images

## Slide 3: Thesis Expectations
AC/PC/VN4 detection on raw (un-oriented) data
Detect all landmarks in oriented data
  Use AC/PC/VN4 locations as features
TL to mini-pigs
  Detection of landmarks on raw (un-oriented) data
Docker-ized apps for inference
Notes: What needs to be added:
BCD was a master’s project  Same quality
Full functioning 51 landmark detection
Image -> landmarks
Ideally trainable on mini-pigs
Metrics & measurments of timing and implementation
Define experiments and data – hyp & conclusions  reasoning for conclusion

## Slide 4: Experiments
Multi-stage detection using AC/PC/VN4 as features
TL multi-stage to mini-pigs
Soft-parameter sharing based on landmark similarity
Learning rate weighting by landmark confidence
TL AC/PC/VN4 conv weights to secondary detection
Supervised Learning approaches
  U-Net Distance Map Prediction
  Classic “AlexNet” Conv/FC -> predicting x, y ,z voxel index
    Potentially two stage -> alignment phase
Notes: Dynamically update direction cosine --> re-orients the image at each iteration
- Issues with rotation
- By updating at each iteration we can ideally minimize the overhead for each agent learning each orientation

## Slide 5: Timeline
Original Goal
  Finish Experiments by Feb 1st
  Finish Writing March 1st
Adjusted Timeline
  Writing and experiments concurrently
    (at least five hrs/week outside normal 20 for writing)
  Finish Writing mid-March
Notes: Need to be done writing
Concerns about march deadlines
-- march 9th is first deposit of thesis vs may 14th
-- schedule time through the summer for revisions
At end of PhD/Masters -> budgeted for a semester – needs to be done in a half semester
Defend on may 14th & get degree in august
A good option to get a little stretch time

## Slide 6: MONAI Contributions
RL Interfaces
  Memory, Agent, LandmarkAgent, LandmarkEnv, Policy, DQNPolicy
Transforms
  ToITKImage, ImagePyramid, LoadCSV, LandmarkExtraction
Notes: Itk supports tensors and array  do not need a ToITKImage function
Add meta data to numpy arrays
Itk python binding
Remote modules in ITK – not supported in core
Slicer is moving to JSON

## Slide 7: Communications - wiki
Goal: Increase accountability for time spent on project components
Daily
  Morning work plan
    Work for the day
  End of day progress report
    Work accomplished
    Blockers
Weekly
  Minimum of one PR including thesis updates

## Slide 8: Academic Advising
Semester Hour Requirements
  I only need Three SH of course work – One Class
Independent Study on RL
  Build from foundations to current research topics
  Deliverables
    Course content for a future contemporary topics
    3-4 Homeworks
    Weekly mini-assignments/mini-projects
    Semester long project
Notes: Concerns about march deadlines
-- march 9th is first deposit of thesis vs may 14th
-- schedule time through the summer for revisions
At end of PhD/Masters -> budgeted for a semester – needs to be done in a half semester
Defend on may 14th & get degree in august
A good option to get a little stretch time